## Sheet1
Me | Name | Predecessors | Work | Duration | Resource Names
| Project |  | 76 hours | 17 days?
| Architecture |  | 16 hours | 2 days? | Jeffery Helm
| ITR | 2 | 20 hours | 10 days? | Jeffery Helm[20%];Rodolfo Chacon[5%]
| BR | 3 | 40 hours | 5 days? | Rodolfo Chacon
| MSOpt solution |  | 178.08 hours | 50 days?
| Provision infrastructure | 3 | 8 hours | 1 day? | Jeffery Helm[33%];Mark Gragasin[33%];Neil Sibug[33%]
| System integration and testing | 11;22;28 | 80 hours | 10 days? | Jeffery Helm[33%];Mark Gragasin[33%];Neil Sibug[33%]
| Deployment | 7 | 8 hours | 1 day? | Jeffery Helm[33%];Mark Gragasin[33%];Neil Sibug[33%]
| UAT | 8 | 74.08 hours | 10 days? | Clark customer[25%];Jeffery Helm[10%];Mark Gragasin[33%];Neil Sibug[33%]
| Release to production | 9 | 8 hours | 1 day? | Jeffery Helm[33%];Mark Gragasin[33%];Neil Sibug[33%]
| DB Loading |  | 828.8 hours | 32 days?
| Define loader architecture | 2 | 16 hours | 2 days? | Jeffery Helm
| Define business logic for Clark site data | 12 | 32 hours | 2 days? | Mark Gragasin;Neil Sibug
| Design and implement datamodel | 2;12 | 84 hours | 5 days? | Jeffery Helm[10%];Mark Gragasin;Neil Sibug
| Design loaders for Clark data | 2;12;13;14 | 84 hours | 5 days? | Jeffery Helm[10%];Mark Gragasin;Neil Sibug
| Implement loaders for Clark data | 15 | 320 hours | 20 days? | Mark Gragasin;Neil Sibug
| Implement and perform unit testing - site loaders | 15;16SS | 16 hours | 1 day? | Mark Gragasin;Neil Sibug
| Design MSOpt results loader | 12 | 84 hours | 5 days? | Jeffery Helm[10%];Mark Gragasin;Neil Sibug
| Implement MSOpt results loader | 18 | 160 hours | 10 days? | Mark Gragasin;Neil Sibug
| Implement and perform unit testing - MSOpt results loader | 18;19SS | 16 hours | 1 day? | Mark Gragasin;Neil Sibug
| Design and code reviews | 14SS;15SS;16SS;19SS | 16.8 hours | 1 day? | Jeffery Helm[10%];Mark Gragasin;Neil Sibug
| DB Extraction |  | 310.4 hours | 17 days?
| Define business logic | 14 | 33.6 hours | 2 days? | Jeffery Helm[10%];Mark Gragasin;Neil Sibug
| Design extraction | 23 | 84 hours | 5 days? | Jeffery Helm[10%];Mark Gragasin;Neil Sibug
| Implement extraction | 24 | 160 hours | 10 days? | Mark Gragasin;Neil Sibug
| Implement and perform unit testing | 24;25SS | 16 hours | 1 day? | Mark Gragasin;Neil Sibug
| Design and code reviews | 24SS;25SS | 16.8 hours | 1 day? | Jeffery Helm[10%];Mark Gragasin;Neil Sibug
| MSOpt |  | 512 hours | 40 days?
| Implement setup hierarchy |  | 120 hours | 15 days? | Youngbum Hur
| Incorporate setup hierarchy changes into TI codebase | 29 | 40 hours | 5 days? | Jeffery Helm
| Test multipass code with Clark Test dataset | 30 | 160 hours | 20 days? | Youngbum Hur
| Harden CSV readers/writers | 2 | 40 hours | 5 days? | Jeffery Helm
| Harden input.txt format and reader | 32 | 16 hours | 2 days? | Jeffery Helm
| Add exception handling | 33 | 40 hours | 5 days? | Jeffery Helm
| Status logging | 34 | 16 hours | 2 days? | Jeffery Helm
| Implement launcher and run management | 35 | 80 hours | 10 days? | Jeffery Helm
| Reporting |  | 420 hours | 25 days?
| Design reporting UI (using TI SFW) | 2;14 | 84 hours | 5 days? | Jeffery Helm[10%];Mark Gragasin;Neil Sibug
| Implement reporting UI | 38 | 320 hours | 20 days? | Mark Gragasin;Neil Sibug
| Implement and perform unit testing | 38;39SS | 16 hours | 1 day? | Mark Gragasin;Neil Sibug