## Actions Items
| Current Status | Remarks | Time Needed (hrs) | Action Type | Action Item | Details
December
2015-12-07 | Completed |  |  | Analysis | Multiple Temperature | Multiple Temperature from tooling but in route single temp only
2015-12-07 | Completed |  |  | Meeting | MSOpt Meeting | analysis recap and methodology
2015-12-07 | Completed |  |  | Analysis | Summary Plan | number of setup change and number no change with the total number of machines is not aligned
2015-12-07 | Completed |  |  | Analysis | Summary Plan | number of loadboard change from initial to optimizer and no change from initial to optimizer with the number of setups
2015-12-07 | Completed |  |  | Wrapper Script | Keydevice uploader | fix bug of optimizer on loading key devices
2015-12-07 | Completed |  |  | Report | Load Board accuracy | Initial Load Board shoud be pulling from the SMSDW, not in the Solution data
2015-12-07 | Completed |  |  | Meeting | Clark Meeting | msopt, set criteria, percentage and targets on how to measure the msopt suggestion vs planner actual changes
2015-12-08 | Completed |  |  | Wrapper Script | Initial Setup | create a backup of initial setup
2015-12-08 | Completed |  |  | Report | Summary by package | create report for the total sum of loadboard by package in wip
2015-12-08 | Completed |  |  | Wrapper Script | Initial Setup | create an override in initial setup file for loadboards that does not contain any wip and replace it with a valid machine with wip
2015-12-08 | Completed |  |  | Analysis | MSOpt | detection of the on the package issue. When the a setup in initalsetup file is not priority
2015-12-08 | Completed |  |  | Wrapper Script | Initial Setup | investigation on blank loadboards on initial setup file, one of this is the testware is missing a loadboards
2015-12-08 | Completed |  |  | Meeting | MSOpt Meeting | test cases in msopt, with regards to start_time and machine_instance on wip
2015-12-08 | Completed |  |  | Analysis | MSOpt Test Scenarios | test and check on removing the start time and machine instance in wip. This caused an error and is a bug of optimizer code
2015-12-08 | Completed |  |  | Analysis | MSOpt Test Scenarios | test and check report on changing the start time to snap shot time on the wip.
2015-12-08 | Completed |  |  | Wrapper Script | device capacity | Change script to adapt and load new device capacity that is provided by planning
2015-12-08 | Completed |  |  | Report | Summary Plan | Initial LoadBoard blanks, fix it by pulling the data from smsdw and overwriting the initial LoadBoard from solution data
2015-12-09 | Completed |  |  | Wrapper Script | wip and route | Detection of wip missing a route
2015-12-09 | Completed |  |  | Wrapper Script | testware | Validate testware source of loadboard using flat file generated vs the website tool for testware
2015-12-09 | Completed |  |  | Report | Summary Plan | Corrected, the hours and wip_post_wb column
2015-12-09 | Completed |  |  | Analysis | Summary Plan | Check and Tally all the valid and questionable setup change done by the optimizer
2015-12-09 | Completed |  |  | Analysis | Machine | Tester Hiararchy issue, check and verify the issue
2015-12-10 | Completed |  |  | Wrapper Script | testware | Correct the script to retain lots that has last been used in testware to have a historical data
2015-12-10 | Completed |  |  | Wrapper Script | WIP | change script to add Time zone correction on the start time
2015-12-10 | Completed |  |  | Analysis | Summary Plan | Check and Tally all the valid and questionable setup change done by the optimizer preparation for the Clark meeting
2015-12-10 | Completed |  |  | Analysis | Temperature validation | Manually from the data and Script from the mysql database, check for temperature mismatch from initialsetup: machine: route and tooling data
2015-12-10 | Completed |  |  | Meeting | Clark Meeting | Presented the optimizer suggested plan, explain each setup change and why the optimizer decides to have a setup change. In addition MSOpt and Clark team forecast the next step of Optimizer project
2015-12-11 | Completed |  |  | Report | Summary Report | Fix bug in blank initialsetup tooling if blank solution pull data from smsdw, blank hours pull data from pph in route.
2015-12-11 | Pending |  |  | Wrapper Script | Temperature correction | Match the temperature of initialsetup and machine to the temperature of route
2015-12-11 | Pending |  |  | Document | Requirements of Enterprise | Document all wrapper scripts and create requirements for the Enterprise based on the wrapper scripts

## Issues
Date | Issue | Effect | Action Item
1 | Data of Parts per hour (PPH) data for each tooling is not updated in the database of CLARK. There is no standard update protocol used for updating the database for parts per hour. The data source is in Excel spreadsheet. Manual Update to spreadsheet to Database | During Optimizer test run. It will produce not the incomplete data if this is not updated. Data Inconsistency will affect the data output of the optimizer | Create an auto email Alert for inconsistency of data and send a report in csv format. Alert concerned personnel to update their data to Database.
December
msopt
1 | Optimizer prioritizing package change over load board change (Change hiararchy Loadboard 4hrs, Package Size 8hrs, Package Type 16hrs) | According to planner package change is costly than loadboard change | This will be a requirement for the Enterprise version
2 | Start and Completion time in the solution file
3 | Start time in WIP is in Dallas Timezone
4 | When Start time and Machine Instance is blank in WIP
5 | The Tooling Family in Solution file is blank, when it is an Initial Lot
6 | Package Type change over Loadboard and change package size (hierarchy: Loadboard, Package Size, Package Type (STD, STRIP))
data
1 | Multiple temperature for a single Loadboard in Tooling file
2 | Temperature mismatch for the initial setup; machine; route and tooling file
3 | Tester hiararchy not update in machine file
4 | source for initial loadboard in twstatus
5 | Key device data did generate properly
6 | Device capacity modify the script and pull the device id based on device alias
7 | WIP file does not have route
8 | Correct the script to retain lots that has last been used in testware to have a historical data
summary plan
1 | Loadboard accuracy from smsdw, also for blank
2 | hours and wip_post_wb

## Activities done
Activities
1
2
3
4
5
6
7
8
9
10
11
12

## Learnings
Learnings
1 | Understand more what the planner expects from Optimizer
2 | Understand how the planner creates plan for the floor
3 | Have an in-depth knowledge on how optimizer process the data
4 | Familiarity for the data sources of optimizer
5 | Identification of data inaccuracy
Proper identification of Device Alias and ID

## Overall Progress
During the stay at TI-CLARK most of our time has been diverted to troubleshooting/fixing CLARK test Input files and Report generation Errors.
After resolving all the current issues with the Optimizer, MSOpt and Clark team decided to have a plausible measurement of optimizer and planner output
Clark management team decided that Optimizer will be a priority on next year's TI-Clark plan
Monitor all deployed scripts.