## Actions Items
| Current Status | Remarks | Time Needed (hrs) | Description
April-May Effort for CLARK
1 | completed | Additional Task | 17 | Auto Email Notification scripts for input files errors.
2 | Completed | Additional Task | 17 | Auto Email for Monitoring scripts in case of errors.
3 | completed | Additional Task | 8.5 | Autorun scripts for running Optimizer in desktop computer of CLARK. With error Notification
4 | completed | Additional Task | 40 | Manual run Script for running Optimizer in desktop computer of CLARK.
5 | completed | Additional Task | 68 | Website for MSOPT tool. For updating/viewing the target key devices and future tool for MSOPT.
6 | completed | Additional Task | 8.5 | Install and setup need libraries need for running automation scripts in Production environment
7 | completed |  | 17 | Documentation of automation scripts and MSOPT website.
8 | completed | Additional Task | 1 | Prepare input files data CLARK to be sent to Shihui MSOPT Team at Dallas for running the optimizer v4 and simulator using CLARK Data sets.
9 | completed |  | 4 | Documentation for the source database/systems of each input files of optimizer to be used for other customer
10 | completed |  | 4 | Presentation of Shishui v4 vs Yumin v1, Yufen v2, Zhufeng v3, zhufeng v3.1. This is to identify if the existing code for each version is still present in the latest version and identify the base code
11 | completed | Additional Task | 5 | Standard email notification for errors in all the scripts and can be triggered in Unix and windows platform
12 | Completed |  | 25.5 | Find source of the errors being generated by optimizer.
13 | completed |  | 8 | design documentation for running optimizer manually and autotmatically
14 | completed | Additional Task | 4 | feasibility document for error detection script modification to add age of extracted data
15 | completed | Additional Task | 8 | Modification of Automated and manual scripts to add Input files in backups
16 | completed |  | 8 | documentation and presentation slides for running optimizer automatically and manually
17 | completed | Additional Task | 16 | Modification of error detectection/email notification to include age of extracted data.
18 | completed | Additional Task | 2 | modification on scripts in detecting ATSS vs loadboard to include SBE-1
19 | completed | Additional Task | 4 | Script to clean wip.csv's start_time column that is causing optimizer to crash.
June-July Effort For CLARK
june | Completed |  | 2 | Worked with CLARK to modifiy input files to increase machine hours to 72 and increase utilization to 100%.
* June | Completed |  | 16 | Worked with CLARK on how to create initial setup input files for the interprise version.
* June | Completed |  | 16 | Created scripts to create initialsetup.csv file using CLARK's parameters
* june | Completed |  | 4 | Worked With CLARK to determine the proper temperature of machine-tooling combination
* june | Completed |  | 16 | Modified scripts for manual and automated run for correcting the temperature for machine-tooling combination. Downloads flat files from RTD and parse the data
* june | Completed |  | 8 | Modified MSOPT tool site for adding history and for each key devices entered
* JUne | Completed |  | 24 | modified scripts for manual and automated run to limit the wip based on the max wipdays configuration. And include configuration that is modified by the user. Eg max wip days
* June | Completed |  | 8 | Modified scripts for manual and automated run to limit the key devices based on the maximum target on the keydevices file.
* June | Completed |  | 4 | Modified scripts for manual and automated run to add a 10% buffer on the keydevice targets be for limiting the wip and sorting wip first by wieght
* june | Completed |  | 4 | traced missing loadboards from initial setup
*july | on going |  | 8 | trace certification not matching on the route files and the tooling file
* July | on going |  | 16 | Add additional features on MSOPT tool site to multiplication value for logpoint and activation option for this feature
* july | on going |  | 16 | Work with clark to determine the wip prior to test
* july | on going |  | 32 | search on the source code of the optimizer yumin the location of 1. Lists all lots that can run in this setup (sorted by weight desceding) – sium all weights that can be done in the time horizon (48 hrs)  this is the benefit of this setup. 2. the lots that quality to run on this setup, and then we optimize creating many possible groups of lots that can run in the 48 hrs or less

## Issues
| Issue | Effect | Action Item
1 | Data of Parts per hour (PPH) data for each tooling is not updated in the database of CLARK. There is no standard update protocol used for updating the database for parts per hour. The data source is in Excel spreadsheet. Manual Update to spreadsheet to Database | During Optimizer test run. It will produce not the incomplete data if this is not updated. Data Inconsistency will affect the data output of the optimizer | Create an auto email Alert for inconsistency of data and send a report in csv format. Alert concerned personnel to update their data to Database.
2 | Data inconsistency between Loadboard and ATSS. Data on the loadboard database and ATSS is not the same | Lots using those loadboards will not be included in the algorithm during the optimizer run as a result data is incomplete | Create an auto email Alert for inconsistency of data and send a report in csv format. Alert concerned personnel to update their data to Database
3 | Data for tester is not found in the tester hierarchy database | Lots with these testers will not be included in the optimizer during run. Data output from optimizer will be inconsistent | Create an auto email Alert for inconsistency of data and send a report in csv format. Alert concerned personnel to update their data to Database
4 | Target for Key devices is not verified | If data given is invalid for key device target, the data output will not be consistent | develop MSOPT tool Website for viewing key devices and possible tools that will be added to the site

## Activities done
Activities
1 | In-depth review of optimizer error output and how are they related to SQL Scripts.
2 | Identify the source of the data inconsistency.
3 | Analyze how data is being populated and the source of the data.
4 | Meeting with data owners and find solutions for data inconsistencies
5 | Meeting with concerned groups to complete needed actions items for optimizer input.
6 | Request, Setup, install and configure production environment (CLARK Machine) for running automated email notification under Solaris
7 | Created perl scripts for automated email notification with report attachments in csv format.
8 | Create script for running optimizer on windows automatically and manually,
9 | Setup, install and configure optimizer environment for running optimizer automatically and manually under windows 7 (CLARK Machine)
10 | Documentation for data source and extraction scripts for optimizer input. This includes how the data is being created.
11 | Verify that all version codes are still present in the latest version of optimizer and set the base source code.
12 | Continued Mapping Shihui code for comparison to Algorithm

## Learnings
Learnings
1 | How the output of optimizer is read by line planners and concerned persons.
2 | How the source tables/databases are being populated by different systems in place.
3 | Inputs from users on features that may be added in the enterprise version

## Overall Progress
During the travel to CLARK most of our time has been diverted to troubleshooting/fixing CLARK test Input files Errors.
Due to that some movement in our schedule (CLARK visit) the simulator model training has not yet started. And we have to squeeze in all delayed deliverable for Quarter 2.
Additional task added:
o For creating the MSOPT tool for Optimizer.
o Scripts for tracking down errors and generating reports.
o Work with the groups concerned on solving some of the optimizer input files problems.
o Provide support for optimizer errors.
Additional customer for Optimizer. That may encounter different problem from CLARK Test. This may require different approach that is different from CLARK.
Monitor all deployed scripts.
During the stay at CLARK we identified the base code of the project and what are some of the requirements needed.