## KT plan
Wipro Engineer 1
Session Topic | SubTopic | Dependencies | Hours Required for KA | End Date (Dalls time) | Time(PI time) | Location | Inputs/Key Docs. | Opportunity to Document SOP | KA complete | Asssessment Result | Incumbent Engineer | TI Engineer | Comments
Cisco Agent & IP Phones | (local/international calls, conference calls, Meet-Me bridges, Voice Mails, Cisco WebEx Connect) - how to process | Access IDs | 1hr | 2015-09-18 | 4pm-5:30pm | Within TI |  | None | Complete
Project Process | process through initial request, research, design, coding, testing, installation,m release | None | 2hr | 2015-10-05 | 4pm-5:30pm | Within TI |  | None | Complete
Project Oveview | 1. High level architecture 2. Overview of interfacing systems 3. Business processes that are implemented 4. Optimizer Versions discussion 5. Overview of Inputs and Outputs | None | 1hr | 2015-10-06 | 4pm-5:30pm | Within TI | In MSOPT Sharepoint | None | Complete
Overview of Optimizer and Simualtion Research Models Algorithms | 1. Optmizer Model Objective 2. Optimizer algorithm high level overview 3. Optimizer Input and Outpus | none | 8hr | 2015-10-09 | 4pm-5:30pm | Within TI | In MSOPT Sharepoint | None | Complete
Environment | 1. Optmizer Unix - Current and Future 2. Simulator XP - Current and Future 3. Setup access to interfacing systems (data feeds) - Current and Future 4. Reporting - Current and Future 5. How to execute Optmizer model 6. How to execute Simulation model | Access Accounts for each system component | 4hr | 2015-10-07 | 4pm-5:30pm | Within TI | In MSOPT Sharepoint | None | Complete
Optimizer and Simulator input Files | 1. Optimizer input files definition 2. Difference of input files per version 3. Simulator Input files definition | Access to source of the optimizer | 4 hrs | 2015-10-08 | 4pm-5:30pm | Within TI |  | None | Complete
Development Environment | 1. Setting Up windows development Environment 2. Accessing source code 3. Using Git | Access to source of the optimizer | 4 hrs | 2015-10-09 | 4pm-5:30pm | Within TI |  | None | Complete
Optimizer Algorithm Step 1.x | 1. Step 1.x Of Algorithm Discussion. 2. Step 1.x psuedo code | Access to Optimizer Sharepoint Site | 16 hrs | 2015-10-09 | 4pm-5:30pm | Within TI | In MSOPT Sharepoint | None | Complete
Optimizer Algorithm Step 2.x | 1. Step 2.x Of Algorithm Discussion. 2. Step 2.x psuedo code | Access to Optimizer Sharepoint Site | 16 hrs | 2015-10-16 | 4pm-5:30pm | Within TI |  | None | Complete
Optimizer Algorithm Step 3.x | 1. Step 3.x Of Algorithm Discussion. 2. Step 3.x psuedo code | Access to Optimizer Sharepoint Site | 16 hrs | 2015-10-23 | 4pm-5:30pm | Within TI |  | None | Complete
Optimizer Source Code | Step 1-3 location on source code | Access to Optimizer Sharepoint Site and GIT | 16 hrs | 2015-10-30 | 4pm-5:30pm | Within TI |  | None | In Progress
Simulator | 1. Custom rule Creation | Access to Optimizer Sharepoint Site | 4 hrs | 2015-10-30 | 4pm-5:30pm | Within TI |  | None
CLARK Wrapper Scripts and User Interface Tool | 1. Wrapper Scripts Overview 2. Input files database 3. Scripts triggers 4. Custom input files Creation 5. Data error Reporting 6. Report generator 7. MSOpt Tool Overview 8. Existing Functions discussion | Access to Clark PC | 8 hrs | 2015-11-15 | 4pm-5:30pm | Within TI |  | None
C++ Training | L2: C ++ training | WiPro@Webex | 30 hrs | 2015-10-16 | 12:30pm-3:30pm | Within TI |  | None | Complete
Perl Training | Perl Scripting training | WiPro@Webex | 15 hrs | 2015-10-09 | 4:30pm-7:30pm | Within TI |  | None | Complete

## Risk,Issue,Action Log
S.No | Risk/Issue/Action | Description | Assigned to | Created Date | Due Date | Status | Remarks
1 | action | identify and install softwares that need on the machines/laptops |  | 2015-09-30 |  | closed
2 | action | identify workarea location |  | 2015-09-30 |  | closed
4 | action | Access to documentation available |  | 2015-09-30 |  | closed
5 | action | All engineers onboard |  | 2015-09-30 |  | closed | Members are on Board
6 | action | Laptops/Desktops with access to n/w available for knowledge acquisition |  | 2015-09-30 |  | closed | Permanent laptops has been issued and able to access network
7 | action | Detailed KT plan completed |  | 2015-09-30 |  | closed
11 | action | All engineers have Xid and access to TI n/w |  | 2015-09-30 |  | closed | Able to login and access TI network
13 | action | Access to application environments - at the least full access to Dev & Test and read to Prod |  | 2015-09-30 |  | closed
14 | action | Names of Wipro engineers included in distribution lists |  | 2015-09-30 |  | closed
15 | action | Complete training on ticketing tool |  | 2015-09-30 |  | closed
16 | action | laptops to be used |  | 2015-09-30 |  | closed
17 | action | SS for Optimizer while breaking down Package Issue code |  | 2015-09-30 |  | closed
18 | action | Understanding of Step 0 of the Optimizer Algorithm and Psuedo code |  | 2015-09-30 | End of KAP | closed
19 | action | Understanding of Step 1.x of the Optimizer Algorithm and Psuedo code |  | 2015-09-30 |  | closed
20 | action | Understanding of Step 2.x of the Optimizer Algorithm and Psuedo code |  | 2015-09-30 | End of KAP | closed
21 | action | Understanding of Step 3.x of the Optimizer Algorithm and Psuedo code |  | 2015-09-30 | End of KAP | closed
22 | action | Identification step 0 on the source code |  | 2015-09-30 | before End of Month | closed
23 | action | Identification step 1.x on the source code |  | 2015-09-30 | before End of Month | open
24 | action | Identification step 2.x on the source code |  | 2015-09-30 | before End of Month | open
25 | action | Identification step 3.x on the source code |  | 2015-09-30 | before End of Month | open
26 | action | Development Environment for windows |  | 2015-09-30 | 1st week of the month | closed
27 | action | Shadow for input files customization for CLARK beta testing |  | 2015-09-30 | End of SS | open
28 | action | VB Script migration to Perl |  | 2015-09-30 | End of SS | open
29 | action | Mysql database used by Prototype to Oracle |  | 2015-09-30 | End of SS | open
30 | action | Propose fix for Package issue |  | 2015-09-30 | before End of Month | open
31 | action | Customize Autosched AP model |  | 2015-09-30 | before End of Month | open
32 | action | Migration of MSOPT tool from FFW to TI Spring |  | 2015-09-30 | end of PS | open

## Schedule
| August 2015 |  | Sept 2015 |  |  |  | October 2015 |  |  |  | Nov 2015 |  |  |  |  | Dec 2015
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W7 | W8 | W9 | W10
| 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
| 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 32
Transition Track | Sept 2015 W5: TRANSITION
Optimizer | Sept 2015 W3: KAP; Nov 2015 W11: SS; Nov 2015 W14: PS